## Action Plan
Department | Owner | Priority | Action | Metric Impacted | Due Date | Supporting Data
Collections | Collections Head | 🔴 Critical | Collections at 0.3% of AOP — below 85% threshold. Gap of ₹11,065,403,000. Activate demand letters and personal outreach. | Collections vs AOP | 08 Jul 2026 | Actual: ₹34,597,000 ¦ Target: ₹11,100,000,000
Collections | Collections Head + Legal (if unresolved) | 🔴 Critical | 52 customer(s) overdue >30 days. ₹29,084,000 at risk. Issue final demand notices. Escalate to legal if no response in 7 days. | Overdue Collections | 05 Jul 2026 | 52 units ¦ ₹29,084,000 outstanding
Collections | Collections Head | 🔴 Critical | Cash-flow leakage: 4 unit(s) where milestone is completed but collection of ₹6,958,000 not yet received. Raise demand notes and collect within 48 hours. | Cash Flow Leakage | 08 Jul 2026 | 4 milestones complete, collections pending
Construction | Construction Head | 🔴 Critical | 6 delayed milestone(s) have no documented Delay Reason. All responsible owners must submit reasons by EOD — required for leadership reporting. | Data Completeness / Construction Tracking | 05 Jul 2026 | Activities: Window frame, Main door, Internal wiring, Lobby finishing, Putty
Construction | Construction Head + Finance | 🔴 Critical | Cost overrun detected in 18 activity/milestone(s). Excess cost of ₹8,713,541 vs plan. Review with Finance and approve change orders. | Cost of Construction (CoC) | 12 Jul 2026 | 18 activities >10% over planned cost
Finance | Finance Head / CFO | 🟡 High | Review NCF bridge plan against AOP GPL Pre-BD NCF target of ₹40,500,000. Ensure cash headroom is adequate given collections shortfall. Defer non-critical outflows. | Net Cash Flow (NCF) | 12 Jul 2026 | AOP NCF Target: ₹40,500,000
Leadership | Project Director | 🟡 High | Pending decision item: 'Approve additional finishing contractor for Aurora Heights'. Linked metric: Construction / CoC. Status: Open. | Construction / CoC | Apr-26 | Recover 10-day delay in finishing milestone
Leadership | Collections Lead | 🟡 High | Pending decision item: 'Finalize collection recovery plan for overdue customers'. Linked metric: Collections. Status: Open. | Collections | Apr-26 | Improve cash inflow by ₹4.5 Cr
Leadership | Sales Head | 🟡 High | Pending decision item: 'Approve launch pricing for Riverstone Park Phase 2'. Linked metric: Sales. Status: In Progress. | Sales | May-26 | Unlock 3BHK sales plan
Leadership | Marketing Lead | 🟡 High | Pending decision item: 'Close additional marketing budget request'. Linked metric: Booking Value. Status: Open. | Booking Value | May-26 | Support Q1 booking target
Leadership | Finance Lead | 🟡 High | Pending decision item: 'Validate cost overrun provision for Vista Grove'. Linked metric: NCF / CoC. Status: Open. | NCF / CoC | Jun-26 | Avoid variance surprise in Q1 CBE
Sales | Rohan Mehta | 🔴 Critical | Sales achievement is only 16.9% of AOP target. Gap of ₹2,791,445,000 must be recovered within this month. | Booking Value vs AOP | 12 Jul 2026 | Actual: ₹568,055,000 ¦ Target: ₹3,359,500,000
Sales | Rohan Mehta | 🟡 High | Product Mix shortfall: 1BHK units — actual 17 vs target 81 (64 units short). Realign sales focus. | 1BHK Product Mix | 12 Jul 2026 | Actual 1BHK: 17 ¦ Target: 81
Sales | Rohan Mehta | 🟡 High | Product Mix shortfall: 2BHK units — actual 49 vs target 153 (104 units short). Realign sales focus. | 2BHK Product Mix | 12 Jul 2026 | Actual 2BHK: 49 ¦ Target: 153
Sales | Rohan Mehta | 🟡 High | Product Mix shortfall: 3BHK units — actual 14 vs target 65 (51 units short). Realign sales focus. | 3BHK Product Mix | 12 Jul 2026 | Actual 3BHK: 14 ¦ Target: 65
Sales | Sales Head | 🟡 High | 13 booking(s) have no Sales Owner assigned. Assign immediately for accountability. | Ownership / Accountability | 05 Jul 2026 | 13 units without owner

## By Department
Department | Priority | Count
Leadership | 🟡 High | 5
Sales | 🟡 High | 4
Collections | 🔴 Critical | 3
Construction | 🔴 Critical | 2
Finance | 🟡 High | 1
Sales | 🔴 Critical | 1