## Sheet1
Communication # | To | Subject | Channel | Draft
1 | Site Leadership Team / CBE Review | Month-End Site Performance & Cash Flow Review — 05 July 2026 | Email | ━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━ DRAFT COMMUNICATION #1 TO: Site Leadership Team / CBE Review FROM: [Your Name] — AI Performance Analytics SUBJECT: Month-End Site Performance & Cash Flow Review — 05 July 2026 CHANNEL: Email / Teams ━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━ Hi Team, Please find below the AI-generated month-end performance summary for your review. ────────────────────────────────────── EXECUTIVE SUMMARY — 05 July 2026 ────────────────────────────────────── SALES 🔴 CRITICAL Actual : ₹ 568,055,000 AOP Target : ₹ 3,359,500,000 Achievement: 16.9% COLLECTIONS 🔴 CRITICAL Actual : ₹ 34,597,000 AOP Target : ₹ 11,100,000,000 Achievement: 0.3% CONSTRUCTION ✅ ON TRACK Actual Avg Progress : 125.5% AOP Plan Progress : 49.0% Achievement : 256.2% NET CASH FLOW Actual NCF : ₹ -753,064,227 ────────────────────────────────────── KEY RISKS ────────────────────────────────────── - 0 unit(s) flagged as High Risk - 52 customer(s) overdue >30 days ¦ ₹29,084,000 at risk - 0 item(s) require CEO-level escalation - 221 data quality issue(s) flagged for human review All detailed reports (cash flow, action plan, data quality, escalation summary) are attached. Please review and confirm actions before the next CBE review session. Regards, [Your Name] [Your Designation] — Godrej Properties
2 | Sales Head | 🔴 URGENT — Sales Booking Shortfall vs AOP — Action Required | Email + Teams | ━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━ DRAFT COMMUNICATION #2 TO: Sales Head FROM: [Your Name] SUBJECT: 🔴 URGENT — Sales Booking Shortfall vs AOP — Action Required CHANNEL: Email + Teams ━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━ Hi [Sales Head Name], This is a formal alert regarding this month's booking performance: Actual Booking Value : ₹568,055,000 AOP Target : ₹3,359,500,000 Achievement : 16.9% ← BELOW 80% THRESHOLD REQUIRED ACTIONS: 1. Share a revised weekly booking forecast by 05 Jul 2026 2. Identify high-potential leads and activate channel partner outreach 3. Resolve all 13 units without an assigned Sales Owner 4. Submit product-mix recovery plan (1BHK / 2BHK / 3BHK split) by this week's review This will be flagged in the leadership CBE deck if not addressed. Please confirm receipt and share updated numbers by EOD. Regards, [Your Name]
3 | Collections Head + Collections Team | 🔴 Overdue Collections — 52 Customers Require Immediate Action | Email + WhatsApp | ━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━ DRAFT COMMUNICATION #3 TO: Collections Head + Collections Team FROM: [Your Name] SUBJECT: 🔴 Overdue Collections — 52 Customers Require Immediate Action CHANNEL: Email + WhatsApp (team) ━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━ Hi Collections Team, The AI analysis has flagged 52 customers with overdue payments >30 days: Total Outstanding Amount at Risk: ₹29,084,000 TOP PRIORITY CUSTOMERS: Customer Name Unit Number Outstanding Amount Days Overdue Kiara Kapoor AGR-B1001 2,670,000.00 51.00 Aarush Talwar AGR-B0407 1,947,000.00 32.00 Dev Desai AGR-D0708 1,827,000.00 63.00 Rudra Suri AGR-C1506 1,728,000.00 83.00 Avni Mathur AGR-D1104 1,443,000.00 38.00 REQUIRED ACTIONS — IMMEDIATE: 1. Issue formal demand notices to all overdue customers TODAY 2. Personal call by Collections Owner within 24 hours 3. If no response in 7 days → escalate to Legal + Site Head 4. Update collection status in the tracker by EOD for leadership review Monthly collections achievement is currently 0.3% — recovery of overdue amounts is critical to meeting the 85% minimum threshold. Regards, [Your Name]
4 | Construction Head + Site Manager | ⚠️ Construction Delay Alert — 19 Milestone(s) Behind Schedule | Teams + Email | ━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━ DRAFT COMMUNICATION #4 TO: Construction Head + Site Manager FROM: [Your Name] SUBJECT: ⚠️ Construction Delay Alert — 19 Milestone(s) Behind Schedule CHANNEL: Teams + Email ━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━ Hi [Construction Head Name], AI analysis has flagged the following construction delays (>15 days behind plan): DELAYED MILESTONES: Activity Delay Days Responsible Owner Window frame 25 Prakash Pawar Window shutter 25 Prakash Pawar Window frame 25 Nilesh More Main door 25 Nilesh More 1st coat paint 18 Nilesh More These delays directly impact: - Customer milestone-linked collection demands - Project cash flow (estimated collection trigger delayed) - Leadership CBE reporting thresholds REQUIRED ACTIONS: 1. Submit delay reason for ALL flagged milestones by EOD TODAY (mandatory for leadership report) 2. Provide revised completion dates and recovery plan by 05 Jul 2026 3. Identify if any additional cost will be incurred (budget vs actual) 4. Confirm if any construction milestones are 100% complete — collections team needs to trigger demands Please expedite this to avoid cross-functional escalation to CEO. Regards, [Your Name]
5 | All Department Heads | ⚠️ Data Clarification Required — 221 Issues Flagged | Email | ━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━ DRAFT COMMUNICATION #5 TO: All Department Heads (Sales, Collections, Construction, Finance) FROM: [Your Name] SUBJECT: ⚠️ Data Clarification Required — 221 Issues Flagged by AI System CHANNEL: Email ━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━ Hi All, The AI data validation engine has flagged 221 data quality issues that require human review and correction before the next leadership report. Please refer to the attached **Data Quality Report** (data_quality_report.xlsx) for the complete list, sorted by severity. Key issue types identified: Category Severity Count Customer Code Mismatch 🔴 High 105 Unit Mismatch 🟡 Medium 39 Missing Owner 🟡 Medium 34 Cash Flow Leakage 🔴 High — Cash Flow Leakage 31 Missing Data — Delay Reason 🔴 High — Clarification Required 6 Milestone Mismatch 🟡 Medium 3 Milestone Mismatch 🔴 High 2 AOP Scale Mismatch 🔴 High — Clarification Required 1 ACTION REQUIRED: - Each department head to review issues in their area - Correct source data in the respective systems - Confirm corrections to [Your Name] by 05 Jul 2026 Data integrity is essential for accurate leadership reporting. Uncorrected items will appear as "Clarification Required" in the CBE deck. Regards, [Your Name]