## Cover & Metadata
Field | Value
Report Title | Month-End Site Performance & Cash Flow Report
Generated On | 05 July 2026
Prepared By | AI Performance Analytics Engine
Report Period | Current Month (as per input files)
Total Units Tracked | 80
Files Processed | Sales, Construction, Collections, AOP Targets
AI Rules Applied | Business Rule Engine (10 rules), Risk Detector, Escalation Engine
Data Quality Issues | 221
Report Tabs | Cover, Scorecard, Escalation, Product Mix, Cash Flow, Action Plan, Decision Items, AI Recommendations, Data Quality

## Executive Scorecard
KPI | Actual | Target (AOP) | Achievement % | RAG Status | Threshold | Comment
Sales — Booking Value Achievement | ₹568,055,000 | ₹3,359,500,000 | 16.9% | 🔴 Red | Green ≥80% ¦ Amber ≥60% ¦ Red <60% | Below 80% AOP — Sales Head action required
Collections — Monthly Achievement | ₹34,597,000 | ₹11,100,000,000 | 0.3% | 🔴 Red | Green ≥85% ¦ Amber ≥65% ¦ Red <65% | Below 85% threshold — Collections Head action required
Construction Progress Achievement | 125.5% avg progress | 49.0% planned progress | 256.2% | 🟢 Green | Green ≥90% ¦ Amber ≥70% ¦ Red <70% | On schedule
Net Cash Flow (NCF) | ₹-753,064,227 | ₹40,500,000 | -1859.4% | 🔴 Red | Green = Positive / on target | NCF negative — review outflows
High Risk Units | 0 | 0 | N/A | 🟢 Green | Green = 0 ¦ Amber ≤5 ¦ Red >5 | No high-risk units
CEO-Level Escalations | 0 | 0 | N/A | 🟢 Green | Green = 0 ¦ Amber ≤2 ¦ Red >2 | No critical escalations
Customers Overdue >30 Days | 52 | 0 | N/A | 🔴 Red | Green = 0 ¦ Amber ≤5 ¦ Red >5 | ₹29,084,000 at risk
Data Quality Issues Flagged | 221 | 0 | N/A | 🔴 Red | Green = 0 ¦ Amber ≤5 ¦ Red >5 | Human clarification required

## Escalation Summary
Status | Project | Unit Number | Customer | Risk Level | Metric Impacted | Escalation To | Suggested Action | Due Date
🔴 Red | Aster Grove Residences | AGR-A2505 | Ira Rastogi | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-A2505 | Ira Rastogi | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-A2505 | Ira Rastogi | Critical | Construction Delay, High Outstanding, Low Collection, Cash Flow Leakage, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-B2407 | Dev Rastogi | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-B2407 | Dev Rastogi | Critical | Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-A2304 | Naina Balan | Critical | Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-A2304 | Naina Balan | Critical | Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-D1405 | Rudra Talwar | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-D1405 | Rudra Talwar | Critical | Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-C1901 | Sara Chopra | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-C1901 | Sara Chopra | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-C1901 | Ira Rastogi Kumar | Critical | Construction Delay, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-B1901 | Aarush Mathur | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-B1901 | Aarush Mathur | Critical | Overdue Collection, High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-B1901 | Aarush Mathur | Critical | High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-C1807 | Eva Talwar | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-C1807 | Eva Talwar | Critical | High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-A0902 | Avni Bajaj | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-A0902 | Avni Bajaj | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-A0902 | Avni Bajaj | Critical | Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-D1508 | Meera Menon | Critical | Overdue Collection, High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-D1508 | Meera Menon | Critical | High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-D1508 | Meera Menon | Critical | Construction Delay, High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-A2201 | Eva Desai | Critical | Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-A2201 | Eva Desai | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-C0801 | Sara Talwar | Critical | High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-C0801 | Sara Talwar | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-C0801 | Sara Talwar | Critical | Construction Delay, High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-C0801 | Sara Talwar | Critical | High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-D2306 | Samar Menon | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-D2306 | Samar Menon | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-B2406 | Misha Saxena | Critical | Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-B2406 | Misha Saxena | Critical | High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-B2406 | Misha Saxena | Critical | High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-A0502 | Dhruv Rastogi | Critical | Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-A0502 | Dhruv Rastogi | Critical | High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-B2703 | Nikhil Khanna | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-B2703 | Nikhil Khanna | Critical | Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-C0405 | Advik Kapadia | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-C0405 | Advik Kapadia | Critical | Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-C0405 | Advik Kapadia | Critical | Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-B1001 | Kiara Kapoor | Critical | Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-B1001 | Kiara Kapoor | Critical | High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-B1001 | Kiara Kapoor | Critical | Construction Delay, High Outstanding, Low Collection, Cash Flow Leakage, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-B1001 | Kiara Kapoor | Critical | Overdue Collection, High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-D2307 | Sara Khanna | Critical | Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-D2307 | Sara Khanna | Critical | High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-C1806 | Yash Desai | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-C1806 | Yash Desai | Critical | Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-C1806 | Yash Desai | Critical | Construction Delay, High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-D0708 | Dev Desai | Critical | Overdue Collection, High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-D0708 | Dev Desai | Critical | Construction Delay, High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-B0407 | Aarush Talwar | Critical | Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-B0407 | Aarush Talwar | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-B0407 | Aarush Talwar | Critical | Overdue Collection, High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-B1606 | Neil Sarin | Critical | Overdue Collection, High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-B1606 | Neil Sarin | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-B0608 | Tara Bedi | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-B0608 | Tara Bedi | Critical | Overdue Collection, High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-A2405 | Misha Walia | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-A2405 | Misha Walia | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-A2405 | Misha Walia | Critical | High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-X9999 | Dev Rastogi | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-X9999 | Kiara Batra | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-X9999 | Kiara Batra | Critical | Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-C2105 | Nikhil Kapadia | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-C2105 | Nikhil Kapadia | Critical | Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-C2105 | Nikhil Kapadia | Critical | High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-C1506 | Rudra Suri | Critical | High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-C1506 | Rudra Suri | Critical | Overdue Collection, High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-C0906 | Naina Kapoor | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-D0502 | Anika Balan | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-D0502 | Anika Balan | Critical | Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-D1101 | Sara Chopra | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-D1101 | Sara Chopra | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-D1101 | Sara Chopra | Critical | Construction Delay, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-D1101 | Sara Chopra | Critical | High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-D0404 | Pihu Mehra | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-C1808 | Ayan Walia | Critical | High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-C1808 | Ayan Walia | Critical | High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-C1808 | Ayan Walia | Critical | Construction Delay, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-D2208 | Anika Chawla | Critical | High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-D2208 | Anika Chawla | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-D2208 | Anika Chawla | Critical | Construction Delay, High Outstanding, Low Collection, Cash Flow Leakage, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-A2607 | Yash Kapoor | Critical | Overdue Collection, High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-A2607 | Yash Kapoor | Critical | High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-B2403 | Aisha Kapoor | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-B2403 | Aisha Kapoor | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-B1404 | Reyansh Ghosh | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-B1404 | Reyansh Ghosh | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-D1606 | Rudra Gill | Critical | High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-D1606 | Rudra Gill | Critical | Construction Delay, High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-B2205 | Sara Balan | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-B2205 | Sara Balan | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-B2205 | Sara Balan | Critical | Construction Delay, High Outstanding, Low Collection, Cash Flow Leakage, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-A2107 | Misha Gill | Critical | Overdue Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-A2107 | Misha Gill | Critical | Overdue Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-A2107 | Misha Gill | Critical | Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-D1104 | Avni Mathur | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-D1104 | Avni Mathur | Critical | Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-D1104 | Avni Mathur | Critical | Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-D1104 | Avni Mathur | Critical | Overdue Collection, High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-C0904 | Dev Menon | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-C0904 | Dev Menon | Critical | Overdue Collection, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026
🔴 Red | Aster Grove Residences | AGR-C0904 | Dev Menon | Critical | High Outstanding, Low Collection, Sales Risk (16.9% of AOP), Collections Risk (0.3% of AOP), Cross-Functional Escalation | CEO / Site Head | Project Head to review and resolve overdue collections + construction delays | 05 Jul 2026

## Product Mix Analysis
Product Type | Units Sold (Actual) | AOP Target Units | Achievement % | RAG
2.5 BHK | 26 |  |  | ⚪ No Target
2 BHK | 23 |  |  | ⚪ No Target
1 BHK | 17 |  |  | ⚪ No Target
3 BHK | 14 |  |  | ⚪ No Target

## Action Plan
Department | Owner | Priority | Action | Metric Impacted | Due Date | Supporting Data
Collections | Collections Head | 🔴 Critical | Collections at 0.3% of AOP — below 85% threshold. Gap of ₹11,065,403,000. Activate demand letters and personal outreach. | Collections vs AOP | 08 Jul 2026 | Actual: ₹34,597,000 ¦ Target: ₹11,100,000,000
Collections | Collections Head + Legal (if unresolved) | 🔴 Critical | 52 customer(s) overdue >30 days. ₹29,084,000 at risk. Issue final demand notices. Escalate to legal if no response in 7 days. | Overdue Collections | 05 Jul 2026 | 52 units ¦ ₹29,084,000 outstanding
Collections | Collections Head | 🔴 Critical | Cash-flow leakage: 4 unit(s) where milestone is completed but collection of ₹6,958,000 not yet received. Raise demand notes and collect within 48 hours. | Cash Flow Leakage | 08 Jul 2026 | 4 milestones complete, collections pending
Construction | Construction Head | 🔴 Critical | 6 delayed milestone(s) have no documented Delay Reason. All responsible owners must submit reasons by EOD — required for leadership reporting. | Data Completeness / Construction Tracking | 05 Jul 2026 | Activities: Window frame, Main door, Internal wiring, Lobby finishing, Putty
Construction | Construction Head + Finance | 🔴 Critical | Cost overrun detected in 18 activity/milestone(s). Excess cost of ₹8,713,541 vs plan. Review with Finance and approve change orders. | Cost of Construction (CoC) | 12 Jul 2026 | 18 activities >10% over planned cost
Finance | Finance Head / CFO | 🟡 High | Review NCF bridge plan against AOP GPL Pre-BD NCF target of ₹40,500,000. Ensure cash headroom is adequate given collections shortfall. Defer non-critical outflows. | Net Cash Flow (NCF) | 12 Jul 2026 | AOP NCF Target: ₹40,500,000
Leadership | Project Director | 🟡 High | Pending decision item: 'Approve additional finishing contractor for Aurora Heights'. Linked metric: Construction / CoC. Status: Open. | Construction / CoC | Apr-26 | Recover 10-day delay in finishing milestone
Leadership | Collections Lead | 🟡 High | Pending decision item: 'Finalize collection recovery plan for overdue customers'. Linked metric: Collections. Status: Open. | Collections | Apr-26 | Improve cash inflow by ₹4.5 Cr
Leadership | Sales Head | 🟡 High | Pending decision item: 'Approve launch pricing for Riverstone Park Phase 2'. Linked metric: Sales. Status: In Progress. | Sales | May-26 | Unlock 3BHK sales plan
Leadership | Marketing Lead | 🟡 High | Pending decision item: 'Close additional marketing budget request'. Linked metric: Booking Value. Status: Open. | Booking Value | May-26 | Support Q1 booking target
Leadership | Finance Lead | 🟡 High | Pending decision item: 'Validate cost overrun provision for Vista Grove'. Linked metric: NCF / CoC. Status: Open. | NCF / CoC | Jun-26 | Avoid variance surprise in Q1 CBE
Sales | Rohan Mehta | 🔴 Critical | Sales achievement is only 16.9% of AOP target. Gap of ₹2,791,445,000 must be recovered within this month. | Booking Value vs AOP | 12 Jul 2026 | Actual: ₹568,055,000 ¦ Target: ₹3,359,500,000
Sales | Rohan Mehta | 🟡 High | Product Mix shortfall: 1BHK units — actual 17 vs target 81 (64 units short). Realign sales focus. | 1BHK Product Mix | 12 Jul 2026 | Actual 1BHK: 17 ¦ Target: 81
Sales | Rohan Mehta | 🟡 High | Product Mix shortfall: 2BHK units — actual 49 vs target 153 (104 units short). Realign sales focus. | 2BHK Product Mix | 12 Jul 2026 | Actual 2BHK: 49 ¦ Target: 153
Sales | Rohan Mehta | 🟡 High | Product Mix shortfall: 3BHK units — actual 14 vs target 65 (51 units short). Realign sales focus. | 3BHK Product Mix | 12 Jul 2026 | Actual 3BHK: 14 ¦ Target: 65
Sales | Sales Head | 🟡 High | 13 booking(s) have no Sales Owner assigned. Assign immediately for accountability. | Ownership / Accountability | 05 Jul 2026 | 13 units without owner

## Decision Items
Decision Item | Linked Metric | Owner | Timeline | Expected Impact | Status | Remark
Approve additional finishing contractor for Aurora Heights | Construction / CoC | Project Director | Apr-26 | Recover 10-day delay in finishing milestone | Open | Escalate if not closed by 20-Apr
Finalize collection recovery plan for overdue customers | Collections | Collections Lead | Apr-26 | Improve cash inflow by ₹4.5 Cr | Open | Required for month-end NCF
Approve launch pricing for Riverstone Park Phase 2 | Sales | Sales Head | May-26 | Unlock 3BHK sales plan | In Progress | Pending leadership review
Close additional marketing budget request | Booking Value | Marketing Lead | May-26 | Support Q1 booking target | Open | Decision required before campaign release
Validate cost overrun provision for Vista Grove | NCF / CoC | Finance Lead | Jun-26 | Avoid variance surprise in Q1 CBE | Open | Needs finance confirmation

## AI Recommendations
Priority | Area | Recommendation | Expected Impact | Owner | Rule Triggered
🔴 1 | Collections Recovery | Activate demand notices for all 52 overdue customers within 24 hours. Priority recovery of ₹29,084,000. | Reduce overdue book; improve NCF this month | Collections Head | Collections overdue >30 days
🔴 2 | Sales Acceleration | Sales achievement at 16.9%. Sales Head to activate channel partners and review pipeline conversion rates. Focus on shortfall product types. | Close gap of ₹2,791,445,000 vs AOP | Sales Head | Sales <80% of AOP
🟡 3 | Construction Milestone Completion | Expedite completion of milestones where collection demands are pending. Each completed milestone unlocks a collection trigger — prioritise these to improve cash flow. | Unlock deferred collections; improve NCF | Construction Head | Cash-flow leakage: milestone complete, collection pending
🟡 4 | Cost Control | Review all construction activities with actual costs >10% above planned. Raise change orders promptly and report to Finance for NCF reforecasting. | Contain CoC within AOP; protect NCF | Construction Head + Finance | CoC overrun >10% of planned
🟡 5 | Data Quality | 221 data issues flagged. All department heads must correct and resubmit data before next cycle. Missing delay reasons must be submitted by EOD. | Accurate reporting; reduce manual reconciliation | All Dept Heads | Data quality checks

## Cash Flow Summary
Metric | Value (₹) | RAG Status
Collections Inflow (Actual) | 66047000 | 🔴
Collections Target (AOP) | 1770000000 | —
Collections Gap | 1703953000 | 🔴
Collection Achievement % | 3.73 | —
Overdue Amount (>30 days) | 29084000 | 🔴
——— | — | —
CoC Outflow — Actual | 179797274 | —
CoC Outflow — Additional Expected | 4813953 | —
Total CoC Outflow | 184611227 | 🟢
CoC Target (AOP) | 1095000000 | —
CoC Overrun % | -83.14 | —
CoC Status | ✅ Within Limit | —
——— | — | —
Other Costs (AOP-based proxy) | 634500000 | —
——— | — | —
Net Cash Flow (Actual) | -753064227 | 🔴
Net Cash Flow Target (AOP — GPL Pre-BD NCF) | 40500000 | —
NCF Variance (Actual vs AOP) | -793564227 | 🔴
NCF Variance % | -1959.42 | —